## Backlog
id | theme | as a/an | I want to… | so that… | notes | acceptance criteria | added in sprint | story points
1 | personalisaton | user | log in either as guest or admin | adminn can have more rights than guest user |  |  | 1 | 5 | As a user, I can log into an account either as admin or guest
2 | personalisaton | user | contact company for questions | contact for questions, inquiries, concerns |  |  | 1 | 20 | As a user, I can contact the company/group
3 | content | admin | save my data | reopen a project |  |  | 1 | 50 | As an Admin, I can save my data
4 | content | admin | edit the canvas by adding and removing shapes | admin can create and edit shpaes and guest can only view |  |  | 1 | 20 | As an admin, I can edit the canvas by adding and removing shapes
5 | content | user | view shapes on the canvas | can view the rendered shapes |  |  | 2 | 50 | As a user, I can view shapes in shapes database on the canvas
6 | content | admin | sort the shpaes by perimeter and area | organize the data |  |  | 2 | 5 | As an admin, I can sort the shapes by perimeter and area
7 | content | admin | read in data from file into vector | automatically create shapes by its data |  |  | 2 | 5 | As an admin, the shapes created can be read into the program from a file
8 | content | admin | move the shapes | move the shpaes around on canvas |  |  | 2 | 20 | As an admin, I can move the shapes on the canvas
9 | content | admin | create a canvas | so guest and admin can view the shapes and for admin, move the shapes |  |  | 2 | 5 | As an Admin, I can create a canvas to display shapes
10 | content | admin | chose font, color, style, for shapes | create the shpaes and change the font, width, color, for aesthetics |  |  | 2 | 20 | As an Admin, I should be able to select the properties for the text such as color, alignment, font family, font size, etc.

## Done
id | theme | as a/an | I want to… | so that… | notes | acceptance criteria | added in sprint | closed in sprint | story points
1 | content | user | log in either as guest or admin | adminn can have more rights than guest user |  |  | 1 | 2 | 20 | As a user, I can log into an account either as admin or guest
2 | content | user | contact company for questions | contact for questions, inquiries, concerns |  |  | 1 | 2 | 30 | As a user, I can contact the company/group
3 | content | admin | save my data | reopen a project |  |  | 1 | 2 | 80 | As an Admin, I can save my data
3 | content | admin | edit the canvas by adding and removing shapes | admin can create and edit shpaes and guest can only view |  |  | 2 | 2 | 80 | As an admin, I can edit the canvas by adding and removing shapes
4 | content | user | view shapes on the canvas | can view the rendered shapes |  |  | 2 | 2 | 10 | As a user, I can view shapes in shapes database on the canvas
[7 empty] | 2 | 2 | 20 | As an admin, I can sort the shapes by perimeter and area
5 | content | admin | read in data from file into vector | automatically create shapes by its data |  |  | 2 | 2 | 20 | As an admin, the shapes created can be read into the program from a file
6 | content | admin | move the shapes | move the shpaes around on canvas |  |  | 2 | 2 | 20 | As an admin, I can move the shapes on the canvas
7 | content | admin | create a canvas | so guest and admin can view the shapes and for admin, move the shapes |  |  | 2 | 2 | 20 | As an Admin, I can create a canvas to display shapes
8 | content | admin | chose font, color, style, for shapes | create the shpaes and change the font, width, color, for aesthetics |  |  | 2 | 2 | 20 | As an Admin, I should be able to select the properties for the text such as color, alignment, font family, font size, etc.

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 200 | 50 | 0 | 40 | 0 | 200
2 | 150 | 20 | 0 | 7 | 0 | 150
|  |  |  | #DIV/0! | 0 | 0
|  |  |  | #DIV/0! | 0 | 0

## Lists
0
5
10
20
30
50
80
130
200
400
1000