## Sprint1
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Sprint Review
As a user, I can log into an account either as admin or guest | Task 1 |  | closed | 5 | 1 | 2 | 2 |  | 0
| Task 2 |  | closed | 2 | 0 | 0 | 2 |  | 0
| Task 3 |  | In Progress | 4 | 0 | 0 | 2 |  | 2
As a user, I can contact the company/group | Task 4 |  | In Progress | 15 | 2 | 4 | 10 |  | 0
| Task 5 |  | In Progress | 25 | 4 | 5 | 15 |  | 0
| task 6 |  | In Progress | 4 | 0 | 0 | 0 |  | 0
| task 7 |  | In Progress | 6 | 4 | 6 |  |  | 0
As an Admin, I can save my data | task 8 |  | In Progress | 10 | 0 | 5 | 5
As an admin, I can edit the canvas by adding and removing shapes | task 9 |  | In Progress | 4 | 0 | 2 | 2 | 5
As a user, I can view shapes in shapes database on the canvas | task 10 |  | In Progress | 10 | 3 | 4 | 3
As an admin, I can sort the shapes by perimeter and area |  |  | In Progress | 75 | 14 | 28 | 41
As an admin, the shapes created can be read into the program from a file
As an admin, I can move the shapes on the canvas
As an Admin, I can create a canvas to display shapes
As an Admin, I should be able to select the properties for the text such as color, alignment, font family, font size, etc.
Sprint Goal
Some sprint goal